## Slide 1: CTNDCI: Identifying the Challenges towards a Distributed Nano Data Center Infrastructure Progress Report I
Katrin Kolb, Katharina Rupp, Mengchu Li, Melanie Hauser, Diana Irmscher, Andreas Scholz
21/11/2017

## Slide 2: Achievements
Continued research
Broadened research scope
Drafted a questionnaire

## Slide 3: Next Steps
Narrowing down scope of challenges we want to take a closer look at
Find balance between amount of challenges and extent of analysis
Interview LRZ and ideally some other expert
Idea: Second Questionnaire to interview ISP

## Slide 4: Deviation From Plan
Original research plan based in paper research
Deviation through interviews
Further deviations might follow

## Slide 5: Research Plan
06.11.17 - Preparation and submission of research proposal
07.11.17 - Presentation of the research proposal
08.11.17 - Start project work: Research on current nano data center models, Questionnaire
20.11.17 - Preparation and submission of progress report I
21.11.17 - Presentation of the progress report I
22.11.17 - Continue the project work: Research on current nano data center models, Interview
12.12.17 - Mid term synchronisation
13.12.17 - Continue the project work: Research for challenges towards a widespread usage in practice
12.01.18 - Preparation and submission of progress report II
13.01.18 - Continue the project work: Evaluation of the research results
26.01.18 - Preparation and submission of final deliverables
30.01.18 - Presentation of final deliverables

## Slide 6: We are looking forward to your input!

## Slide 7: References
[1] Green IT Logo:
https://media.licdn.com/mpr/mpr/p/2/005/068/158/3086cb8.jpg
[2] Sonstige Icons:
https://www.flaticon.com/